## Feedback
Feedback each week
Week | No | Feedback | Implemented | Status
Week 1 | 1 | Get feedback from the audience | ☑ | Done
Week 1 | 2 | Make the project for everyone instead of only international students | ☑ | Done
Week 1 | 3 | Don't categorise people | ☑ | Done
Week 1 | 4 | Recommending where to live is a big responsibility | ☐ | In progress
Week 1 | 5 | Test if the data provided by the model is actually accurate | ☐ | In progress
Week 1 | 6 | Commute time may vary depending on the situation | ☐ | In progress
Week 1 | 7 | Make diagrams bigger in the presentation | ☑ | Done
Week 1 | 8 | Do the survey at the start | ☑ | Done
Week 1 | 9 | Meet every day | ☑ | In progress
Week 1 | 10 | The system shouldn't always favour one area | ☐ | In progress
Week 1 | 11 | Where are we going to get the data from? | ☑ | Done
Week 1 | 12 | Subdivide the parts of particular areas | ☐ | In progress
Week 1 | 13 | FastAPI needs to be replaced | ☑ | Done
Week 1 | 14 | Use an enterprise database | ☐ | In progress
Week 1 | 15 | Does the hosting have enough capacity? | ☑ | Done
Week 1 | 16 | Learn from other projects like Rent Made Easy | ☐ | In progress
Week 1 | 17 | Create a profile of each place | ☑ | Done
Week 1 | 18 | Make sure we have permission to use the data | ☐ | In progress
Week 1 | 19 | Take a look at the Google API | ☐ | In progress
Week 2
Week 2 | 1 | Update the group repo on GitHub every day | ☑ | In progress
Week 2 | 2 | GitHub marks start next week, don't miss them | ☑ | In progress
Week 2 | 3 | Record meeting minutes in GitHub | ☑ | Done
Week 2 | 4 | Document next steps discussed by each member | ☑ | Done
Week 2 | 5 | Share project management | ☑ | Done
Week 2 | 6 | Take responsibility for meetings | ☑ | Done
Week 2 | 7 | Everyone needs to contribute to everything | ☑ | Done
Week 2 | 8 | Neon needs to be discussed, possibly change | ☑ | Done
Week 2 | 9 | Free cloud services need to be discussed, possibly change | ☑ | Done
Week 2 | 10 | Separate folders for meetings and project management | ☑ | Done
Week 2 | 11 | Need to set up a research team | ☑ | Done
Week 2 | 12 | Everything should be clean, with a proper layout and well documented | ☑ | In progress
Week 2 | 13 | Feedback needs to be addressed each week | ☑ | In progress
Week 2 | 14 | Look into subsets of areas such as electoral divisions | ☐ | In progress
Week 2 | 15 | Get data from local elections, crime stats, garda, rate my area | ☑ | Done
Week 2 | 16 | Present live working code next week by generating a link | ☑ | Done
Week 2 | 17 | Don't show too much info on the site, only what the user wants | ☐ | In progress
Week 3
Week 3 | 1 | Get the frontend done | ☐ | Done
Week 3 | 2 | Implement safety of the area | ☐ | Not started
Week 3 | 3 | Something easy like a slider for choosing priorities | ☐ | In progress
Week 3 | 4 | Validate it with people | ☐ | In progress
Week 3 | 5 | Let the user choose factors | ☑ | Done
Week 3 | 6 | People will pay more for a safe area | ☐ | Not started
Week 3 | 7 | An attractive website should be the number 1 priority | ☐ | In progress
Week 3 | 8 | Frontend should be done next week | ☐ | In progress
Week 3 | 9 | Need more complexity in the model | ☐ | In progress
Week 3 | 10 | Include pictures of Dublin to give a feel for it | ☐ | In progress
Week 3 | 11 | Evaluate the protocol | ☐ | In progress
Week 3 | 12 | Public transport should be taken into consideration | ☑ | Done